## Sheet1
Design Task
SR. No. | Project | Developer Name | Date | Task Name | Start Time | End Time | Total Time | Status | Remark
1 | Pashuhaat | Ravinsan Kumar | 2022-07-12 | Seeds & Complete Booking & Payment Gatway | 10:00 | 7:00 | 8 Hours | Done
2 | Pashuhaat | Ravinsan Kumar | 2022-07-14 | Changes in Booking Animal | 10:00 | 11:00 | 1 Hours | Done
3 | Pashuhaat | Ravinsan Kumar | 2022-07-14 | Doctor Login Api | 11:00 | 12:00 | 1 Hours | Done
4 | Pashuhaat | Ravinsan Kumar | 2022-07-14 | Send OTP and Verify OTP API | 12:00 | 1:00 | 1 Hours | Done
5 | Pashuhaat | Ravinsan Kumar | 2022-07-14 | Logout api and create middleware and check auth and set auth | 2:00 | 7:00 | 5 Hours | Done
6 | Pashuhaat | Ravinsan Kumar | 2022-07-15 | Checking login and logout of doctor api | 10:00 | 12:00 | 2 Hours | Done
7 | Pashuhaat | Ravinsan Kumar | 2022-07-15 | Get shedule pending list api | 12:00 | 1:00 | 1 Hours | Done
8 | Pashuhaat | Ravinsan Kumar | 2022-07-15 | Get shedule done list api | 2:00 | 4:00 | 2 Hours | Done
9 | Pashuhaat | Ravinsan Kumar | 2022-07-15 | Get treatment pending list | 4:00 | 5:30 | 1:30 Hours | Done
10 | Pashuhaat | Ravinsan Kumar | 2022-07-15 | Get done treatment list | 5:30 | 7:00 | 1:30 Hours | Done
11 | Pashuhaat | Ravinsan Kumar | 2022-07-18 | Get doctor treatment api | 11:00 | 1:00 | 2:00 Hours | Done
12 | Pashuhaat | Ravinsan Kumar | 2022-07-18 | Change treatment status | 2:00 | 3:00 | 1:00 Hours | Done
13 | Pashuhaat | Ravinsan Kumar | 2022-07-18 | Store treatment details | 3:00 | 6:00 | 3:00 Hours | Done
13 | Pashuhaat | Ravinsan Kumar | 2022-07-18 | Get the Shedule list | 6:00 | 7:00 | 1:00 Hours | Done
14 | Pashuhaat | Ravinsan Kumar | 2022-07-19 | Get doctor schedule api | 10:00 | 12:00 | 2:00 Hours | Done
15 | Pashuhaat | Ravinsan Kumar | 2022-07-19 | Change status in doctor schedule api | 12:00 | 1:00 | 1:00 Hours | Done
16 | Pashuhaat | Ravinsan Kumar | 2022-07-19 | Changes in treatment api | 2:00 | 3:00 | 1:00 Hours | Done
17 | Pashuhaat | Ravinsan Kumar | 2022-07-19 | Get doctor details api | 3:00 | 6:00 | 3:00 Hours | Done
18 | Pashuhaat | Ravinsan Kumar | 2022-07-19 | Get doctor fee gatway | 6:00 | 7:00 | 1:00 Hours | Not Done
19 | Pashuhaat | Ravinsan Kumar | 2022-07-20 | Doctor Payment Gateway | 10:00 | 12:00 | 2:00 Hours | Done
20 | Pashuhaat | Ravinsan Kumar | 2022-07-20 | Store Doctor Payment Success | 12:00 | 2:00 | 2:00 Hours | Done
21 | Pashuhaat | Ravinsan Kumar | 2022-07-20 | Error solving in some api | 2:00 | 4:30 | 2:30 Hours | Done
22 | Pashuhaat | Ravinsan Kumar | 2022-07-20 | Rating and review store | 4:30 | 6:30 | 2:00 Hours | Done
23 | Pashuhaat | Ravinsan Kumar | 2022-07-20 | Send push notification of firebox | 6:30 | 7:00 | 0:30 Hours | Not Done
24 | Pashuhaat | Ravinsan Kumar | 2022-07-21 | Device Token save | 10:05 | 11:00 | 1:00 Hours | Done
25 | Pashuhaat | Ravinsan Kumar | 2022-07-21 | Create database table and make model | 11:00 | 1:00 | 2:00 Hours | Done
26 | Pashuhaat | Ravinsan Kumar | 2022-07-21 | Send push notification of firebox | 2:00 | 6:00 | 4:00 Hours | Done
27 | Pashuhaat | Ravinsan Kumar | 2022-07-21 | Create Localization | 6:00 | 7:00 | 1:00 Hours | Done
28 | Pashuhaat | Ravinsan Kumar | 2022-07-22 | Changes in get animal details | 10:00 | 12:00 | 2:00 Hours | Done
29 | Pashuhaat | Ravinsan Kumar | 2022-07-22 | Changes review and rating api | 12:00 | 1:00 | 1:00 Hours | Done
30 | Pashuhaat | Ravinsan Kumar | 2022-07-22 | Create Push notification with firebase | 2:00 | 3:00 | 1:00 Hours | Done
31 | Pashuhaat | Ravinsan Kumar | 2022-07-22 | Set Notification all controller's functino | 3:00 | 6:00 | 3:00 Hours | Done
32 | Pashuhaat | Ravinsan Kumar | 2022-07-22 | Get Notification all by user | 6:00 | 7:00 | 1:00 Hours | Done
33 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | Set Notification for doctor | 10:30 | 11:30 | 1:00 Hours | Done
34 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | Get Notification for doctor by firebase | 11:30 | 1:00 | 1:30 Hours | Done
35 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | Set the notification message of all store and send doctor shedule an treatment status change | 2:00 | 3:00 | 1:00 Hours | Done
36 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | fitlter all treatment and doctor schedule list | 3:00 | 5:00 | 2:00 Hours | Done
37 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | filter of product list | 5:00 | 6:00 | 1:00 Hours | Done
38 | Pashuhaat | Ravinsan Kumar | 2022-07-25 | filter of booking list | 6:00 | 7:00 | 1:00 Hours | Done
39 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | Filter of treatment pending | 10:00 | 11:30 | 1:30 Hours | Done
40 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | Filter of treatment Done | 11:30 | 1:00 | 1:30 Hours | Done
41 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | Filter of appoinment pending | 2:00 | 4:00 | 2:00 Hours | Done
42 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | Filter of appoinment Done | 4:00 | 5:00 | 1:00 Hours | Done
43 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | Make booking invoice | 5:00 | 6:00 | 1:00 Hours | Done
44 | Pashuhaat | Ravinsan Kumar | 2022-07-26 | calculate distance of animal near | 6:00 | 7:00 | 1:00 Hours | Done
45 | Pashuhaat | Ravinsan Kumar | 2022-07-27 | Set the Distance api of geolocation | 10:00 | 5:00 | 6:00 Hours | Done
46 | Pashuhaat | Ravinsan Kumar | 2022-07-27 | calculate distance of near animal | 5:00 | 7:00 | 2:00 Hours | Done
47 | Pashuhaat | Ravinsan Kumar | 2022-07-28 | Calculate Location in km from current Location and search location | 10:00 | 1:00 | 3:00 Hours | Done
48 | Pashuhaat | Ravinsan Kumar | 2022-07-28 | Api of banking details of user | 2:00 | 3:00 | 1:00 Hours | Done
49 | Pashuhaat | Ravinsan Kumar | 2022-07-28 | Laravel install for acorbiz documenttation | 3:00 | 7:00 | 4:00 Hours | Done
50 | Corpbiz | Ravinsan Kumar | 2022-07-29 | Setting the Admin and guard | 10:00 | 3:00 | 4:00 Hours | Done
51 | Corpbiz | Ravinsan Kumar | 2022-07-29 | Create Migration and database | 3:00 | 5:00 | 2:00 Hours | Done
52 | Pashuhaat | Ravinsan Kumar | 2022-07-29 | SET LOCALIZATION | 5:00 | 7:00 | 2:00 Hours | Done
53 | Pashuhaat | Ravinsan Kumar | 2022-08-01 | SET LOCALIZATION | 10:00 | 11:00 | 1:00 Hours | Done
54 | Pashuhaat | Ravinsan Kumar | 2022-08-01 | Set localization data english and hindi | 11:00 | 1:00 | 2:00 Hours | Done
55 | Pashuhaat | Ravinsan Kumar | 2022-08-01 | Roles And Permission | 2:00 | 7:00 | 5:00 Hours | Done
56 | Pashuhaat | Ravinsan Kumar | 2022-08-02 | Create role database and permission database also more database releated with this and also crud of role and permission also | 10:00 | 7:00 | 8:00 Hours | Not Done
57 | Pashuhaat | Ravinsan Kumar | 2022-08-03 | Create role database and permission database also more database releated with this and also crud of role and permission also | 10:00 | 7:00 | 8:00 Hours | Not Done
58 | Pashuhaat | Ravinsan Kumar | 2022-08-04 | Roles and Permission and create middlware and crud of menu, crud of Roles and crud permission | 10:00 | 7:00 | 8:00 Hours | Done
59 | Pashuhaat | Ravinsan Kumar | 2022-08-05 | Set the route name in all url | 10:00 | 3:00 | 4:00 Hours | Done
60 | Pashuhaat | Ravinsan Kumar | 2022-08-05 | and entry the menu name and route name | 3:00 | 7:00 | 4:00 Hours | Done
61 | Pashuhaat | Ravinsan Kumar | 2022-08-08 | Create the records of permission of all menu add, view, edit, update and delete | 10:00 | 3:00 | 4:00 Hours | Done
62 | Pashuhaat | Ravinsan Kumar | 2022-08-08 | Make the dynamic menu | 3:00 | 5:00 | 2:00 Hours | Done
63 | Pashuhaat | Ravinsan Kumar | 2022-08-08 | Make the dynamic route of all menu add, view, edit, update and delete | 5:00 | 7:00 | 2:00 Hours | Done
64 | Pashuhaat | Ravinsan Kumar | 2022-08-09 | Create Search api for doctor | 10:00 | 12:00 | 2:00 Hours | Done
65 | Pashuhaat | Ravinsan Kumar | 2022-08-09 | Create Middleware for roles and permission | 12:00 | 3:00 | 2:00 Hours | Done
66 | Pashuhaat | Ravinsan Kumar | 2022-08-09 | And set the middleware in controller and set the condition for permission add, view, edit and delete | 3:00 | 5:00 | 2:00 Hours | Done
67 | Pashuhaat | Ravinsan Kumar | 2022-08-09 | Corbiz Setup | 5:00 | 7:00 | 2:00 Hours | Done
68 | Pashuhaat | Ravinsan Kumar | 2022-08-16 | Set route and middleware for roles and permission | 10:00 | 1:00 | 3:00 Hours | Done
69 | Pashuhaat | Ravinsan Kumar | 2022-08-16 | Set the created at time in all database table | 2:00 | 4:00 | 2:00 Hours | Done
70 | Pashuhaat | Ravinsan Kumar | 2022-08-16 | Set the permission or not if costomer active or not | 4:00 | 6:00 | 2:00 Hours | Done
71 | Pashuhaat | Ravinsan Kumar | 2022-08-16 | Set the permission or not if DOCTOR active or not | 6:00 | 7:00 | 1:00 Hours | Done
72 | Pashuhaat | Ravinsan Kumar | 2022-08-17 | Update route name for role and permission | 10:00 | 3:00 | 4:00 Hours | Done
73 | Pashuhaat | Ravinsan Kumar | 2022-08-17 | bugs fixing in api | 3:00 | 5:00 | 2:00 Hours | Done
74 | Corpbiz | Ravinsan Kumar | 2022-08-17 | crud of category | 5:00 | 7:00 | 2:00 Hours | Done
75 | Pashuhaat | Ravinsan Kumar | 2022-08-18 | Too many bog fix | 10:00 | 7:00 | 8:00 Hours | Done
76 | Pashuhaat | Ravinsan Kumar | 2022-08-19 | Add Whatsapp link in animal detals | 10:00 | 12:00 | 2:00 Hours | Done
77 | Pashuhaat | Ravinsan Kumar | 2022-08-19 | add whatsapp share link animal details | 12:00 | 3:00 | 2:00 Hours | Done
78 | Pashuhaat | Ravinsan Kumar | 2022-08-19 | Add Whatsapp link in latest animal list | 3:00 | 5:00 | 2:00 Hours | Done
79 | Pashuhaat | Ravinsan Kumar | 2022-08-19 | add whatsapp share latest animal list link animal details | 5:00 | 6:00 | 1:00 Hours | Done
80 | Pashuhaat | Ravinsan Kumar | 2022-08-19 | Add condition of doctor activate without day and time schedule not activate doctor | 6:00 | 7:00 | 1:00 Hours | Done
81 | Pashuhaat | Ravinsan Kumar | 2022-08-22 | Add gender status in animal list | 10:00 | 11:00 | 1:00 Hours | Done
82 | Pashuhaat | Ravinsan Kumar | 2022-08-22 | show the notification message in user and doctor side | 11:00 | 3:00 | 3:00 Hours | Done
83 | Pashuhaat | Ravinsan Kumar | 2022-08-22 | show the list of doctor tretmnet pending and done | 3:00 | 5:00 | 2:00 Hours | Done
84 | Pashuhaat | Ravinsan Kumar | 2022-08-22 | show the list customer treatment pending and done | 5:00 | 7:00 | 2:00 Hours | Done
85 | Pashuhaat | Ravinsan Kumar | 2022-08-23 | Many bogs fix in api | 10:00 | 4:00 | 5:00 Hours | Done
86 | Pashuhaat | Ravinsan Kumar | 2022-08-23 | crud of Document center with database and request validation | 4:00 | 7:00 | 2:00 Hours | Done
87 | Corpbiz | Ravinsan Kumar | 2022-08-24 | Pashu id send in api list pending treatment | 10:00 | 12:00 | 2:00 Hours | Done
88 | Corpbiz | Ravinsan Kumar | 2022-08-24 | more bugs fix in admin and api | 12:00 | 3:00 | 2:00 Hours | Done
89 | Corpbiz | Ravinsan Kumar | 2022-08-24 | crud of permission | 3:00 | 5:00 | 2:00 Hours | Done
90 | Corpbiz | Ravinsan Kumar | 2022-08-24 | status and edit and delete set in corpbiz | 5:00 | 7:00 | 2:00 Hours | Done
91 | Pashuhaat | Ravinsan Kumar | 2022-08-25 | Rename Schedule day and time | 10:00 | 11:00 | 1:00 Hours | Done
92 | Pashuhaat | Ravinsan Kumar | 2022-08-25 | View count in latest animal list | 11:00 | 12:00 | 1:00 Hours | Done
93 | Pashuhaat | Ravinsan Kumar | 2022-08-25 | Remove hi and seller name in whatsapp from every place | 12:00 | 3:00 | 2:00 Hours | Done
94 | Pashuhaat | Ravinsan Kumar | 2022-08-25 | When treatment in pending then send notification | 3:00 | 5:00 | 2:00 Hours | Done
95 | Pashuhaat | Ravinsan Kumar | 2022-08-25 | Update rating and review | 5:00 | 7:00 | 2:00 Hours | Done
96 | Pashuhaat | Ravinsan Kumar | 2022-08-26 | Add functionality when user one time create review | 10:00 | 11:00 | 1:00 Hours | Done
97 | Pashuhaat | Ravinsan Kumar | 2022-08-26 | bugs fixing in api | 11:00 | 5:00 | 5:00 Hours | Done
98 | Corpbiz | Ravinsan Kumar | 2022-08-26 | Working on content page | 5:00 | 7:00 | 2:00 Hours | Done
99 | Pashuhaat | Ravinsan Kumar | 2022-08-29 | Working on all bugs fix which is provided by deepak and suraj | 10:00 | 7:00 | 8:00 Hours | Done
100 | Pashuhaat | Ravinsan Kumar | 2022-08-30 | Working on get total notification | 10:00 | 12:00 | 2:00 Hours | Done
101 | Pashuhaat | Ravinsan Kumar | 2022-08-30 | add read unread notification for doctor and user | 12:00 | 3:00 | 2:00 Hours | Done
102 | Pashuhaat | Ravinsan Kumar | 2022-08-30 | create pending appointement to book appointment after status is pending | 3:00 | 5:00 | 2:00 Hours | Done
103 | Pashuhaat | Ravinsan Kumar | 2022-08-30 | Pending treatment list appoinment | 5:00 | 7:00 | 2:00 Hours | Done
104 | Pashuhaat | Ravinsan Kumar | 2022-08-31 | bugs fixing in api | 10:00 | 3:00 | 4:00 Hours | Done
105 | Corpbiz | Ravinsan Kumar | 2022-08-31 | Crud of content page and also status change | 3:00 | 7:00 | 4:00 Hours | Done
106 | Corpbiz | Ravinsan Kumar | 2022-09-01 | Work on every page for change message and add toaster | 10:00 | 3:00 | 4:00 Hours | Done
107 | Pashuhaat | Ravinsan Kumar | 2022-09-01 | Work Pashuhaat bugs and also check with team and sir | 3:00 | 7:00 | 4:00 Hours | Done
108 | Pashuhaat | Ravinsan Kumar | 2022-09-02 | Work Pashuhaat bugs and also check with team and sir and Meeting with team | 10:00 | 3:00 | 4:00 Hours | Done
109 | Corpbiz | Ravinsan Kumar | 2022-09-02 | Working on corbiz seo page with database | 3:00 | 7:00 | 4:00 Hours | Done
110 | Pashuhaat | Ravinsan Kumar | 2022-09-03 | Work latest animal list api change in subcategory slug | 12:30 | 3:00 | 2:30 Hours | Done
111 | Corpbiz | Ravinsan Kumar | 2022-09-03 | Add category name in wish list | 3:00 | 4:00 | 1:00 Hours | Done
112 | Corpbiz | Ravinsan Kumar | 2022-09-03 | crud of seo management | 4:00 | 6:00 | 2:00 Hours | Done
113 | Corpbiz | Ravinsan Kumar | 2022-09-05 | Set permission of seo | 10:00 | 3:00 | 4:00 Hours | Done
114 | Pashuhaat | Ravinsan Kumar | 2022-09-05 | bugs fixing in api and data changes in server | 3:00 | 7:00 | 4:00 Hours | Done
115 | Pashuhaat | Ravinsan Kumar | 2022-09-06 | bugs fixing in api and data changes | 10:00 | 3:00 | 4:00 Hours | Done
116 | Pashuhaat | Ravinsan Kumar | 2022-09-06 | Working on s3 for data storege | 3:00 | 7:00 | 4:00 Hours | Done
117 | Pashuhaat | Ravinsan Kumar | 2022-09-07 | Work on s3 for data storege | 10:00 | 3:00 | 4:00 Hours | Done
118 | Pashuhaat | Ravinsan Kumar | 2022-09-07 | Image and video upload on all pages | 3:00 | 5:00 | 2:00 Hours | Done
119 | Pashuhaat | Ravinsan Kumar | 2022-09-07 | remove all image url link of all pages | 5:00 | 7:00 | 2:00 Hours | Done
120 | Corpbiz | Ravinsan Kumar | 2022-09-08 | url change in api | 10:00 | 11:00 | 1:00 Hours | Done
121 | Corpbiz | Ravinsan Kumar | 2022-09-08 | Set frontend pages of corpbiz and help on ankit | 11:00 | 7:00 | 7:00 Hours | Done
122 | Corpbiz | Ravinsan Kumar | 2022-09-19 | Show Category list and subcategory list | 10:00 | 1:00 | 3:00 Hours | Done
123 | Corpbiz | Ravinsan Kumar | 2022-09-19 | show document list | 2:00 | 5:00 | 3:00 Hours | Done
124 | Corpbiz | Ravinsan Kumar | 2022-09-19 | show document details | 5:00 | 7:00 | 2:00 Hours | Done
Note on H4: Enterslice:
Note on F7: Enterslice: